| 6 to 12 Months Ahead |
| --- |
|  | Appoint a chairperson |
|  | Identify and organize Planning Committee |
|  | Determine sub-committees/sub-committee chairpersons |
|  | Set outreach event goals and benchmarks |
|  | Choose a theme |
|  | Visit potential sites; choose site (develop alternative site if event is outdoors) |
|  | Finance committee drafts initial budget for approval |
|  | Gather cost estimates (site rental, food, drinks, sound/lights, etc.) |
|  | Request recommendations for entertainment; hold auditions if necessary |
|  | Gather bids for entertainment, decorations, design, printing and other major items |
|  | Decide on admission cost and create sponsorship amounts/levels |
|  | Set marketing/public relations schedule |
|  | Develop press release and calendar listings |
|  | List items to be underwritten and possible sources |
|  | Research/approach honorees if appropriate for specified outreach event |
|  | Compile mailing list (individuals/businesses) |
|  | Get written contracts for site, entertainment, etc. |
|  | Check proposed date for potential conflicts; finalize date in writing |
|  | Select photographer; arrange for photos of VIPs, chairperson, honorees, etc. |
|  | Get biographical information on VIPs, celebrities, honorees, chairperson, etc. |
|  | Pick graphic artist; begin invitation design |
|  | Create logo for event with graphic artist |
|  | Order hold-the-date cards or other event announcements |
|  | Invite/confirm VIPs |
|  | Investigate need for special permits, licenses, insurance, etc. |

| 4 to 6 Months Ahead |
| --- |
|  | Begin regular committee meetings |
|  | Send requests for funding or underwriting to major donors, corporations, sponsors |
|  | Request logos from corporate sponsors for printing |
|  | Review with graphic artist invitations, programs, posters, etc. |
|  | Prepare final copy for invitations, return card, posters |
|  | Prepare final copy for tickets |
|  | Complete mailing lists for invitations |
|  | Order invitations, posters, tickets, etc. |
|  | Sign contract with entertainment company |
|  | Make list of locations for posters |
|  | Finalize mailing lists; begin soliciting corporations and major donors |
|  | Obtain lists from honorees, VIPs |
|  | Obtain radio/TV sponsors, public service announcements, promos |
|  | Set menu with caterer for food and beverages |
|  | Secure permits and insurance |
|  | Get written confirmation of celebrity participation/special needs |
|  | Finalize audio/visual contract |
|  | Select/order trophies/awards |
|  | Mail save the date cards |

| 3 to 2 Months Ahead |
| --- |
|  | Assemble/address invitations |
|  | Mail invitations |
|  | Distribute posters |
|  | Finalize transportation/hotel accommodations for staff, VIPs, honorees |
|  | Obtain contracts for decorations and rental items |
|  | Confirm TV/radio participation |
|  | Disseminate press releases regarding celebrities, VIPs and/or honorees |
|  | Follow up to confirm sponsorships and underwriting |
|  | Obtain logos from corporate sponsors for program printing |
|  | Review needs for signs at registration, directional, etc. |
|  | All major chairpersons to finalize plans |
|  | Hold walk-through of event with responsible committees, chairpersons and site staff |
|  | Review/finalize budget, task sheets and tentative timeline |
|  | Start phone follow-up for table sponsors (corporate, VIP, committee) |

| 1 Month Ahead |
| --- |
|  | Phone follow-up of mailing list (ticket sales) |
|  | Place newspaper ads, follow up with news media, on-air announcements |
|  | Confirm staff for registration, hosting, other |
|  | Write to VIPs, celebrities, program participants to confirm participation |
|  | Complete list of contents for VIP welcome packets |
|  | Get enlarged site plan/room diagram, assign seats/tables |
|  | Give estimate of guests expected to caterer/food service |
|  | Meet with all outside vendors, consultants to coordinate event |
|  | Review script/timeline |
|  | Continue assigning seats; set head table, speaker's platform |
|  | Confirm transportation schedules: airlines, trains, buses, cars |
|  | Confirm hotel accommodations |
|  | Confirm special security needed for VIPs, event |
|  | Prepare welcome packet for VIPs, chairperson, and key staff |
|  | Schedule deliveries of special equipment, rentals |
|  | Confirm setup and tear down times with event site |
|  | Finalize plans with party decorator |
|  | Give caterer revised numbers |
|  | Meet with chairpersons, key staff to finalize any of the above |

| 1 Week Before |
| --- |
|  | Meet with all committees for last-minute details |
|  | Finish phone follow-ups |
|  | Confirm number attending |
|  | Finish seating/table arrangements |
|  | Hold training session with volunteers; finalize assignments |
|  | Secure two or three volunteers to assist with emergencies |
|  | Finalize registration staff |
|  | Distribute seating chart; assignments to hosts |
|  | Schedule pickup or delivery of any rented or loaned equipment |
|  | Double-check arrival time and delivery times with vendors |
|  | Reconfirm event site, hotel, transportation, etc. |
|  | Deliver final scripts/ timelines to all program participants |
|  | Finalize catering guarantee, refreshments, etc. |
|  | Confirm number of volunteers |
|  | Make follow-up calls to news media for advance and event coverage |
|  | Distribute additional fliers |
|  | Final walk-through with all personnel |
|  | Schedule rehearsals |
|  | Schedule volunteer assignments for day of event |
|  | Establish amount of petty cash needed for tips and emergencies |
|  | Write checks for payments to be made for the day of the event |

| Day Before Event |
| --- |
|  | Recheck all equipment and supplies to be brought to the event |
|  | Have petty cash and vendor checks prepared |

| Event Day |
| --- |
|  | Arrive early |
|  | Unpack equipment, supplies and make sure nothing is missing |
|  | Be sure all VIPs are in place and have scripts |
|  | Reconfirm refreshments/meal schedule for volunteers |
|  | Go over all the final details with caterer and setup staff |
|  | Check with volunteers to make sure all tasks are covered |
|  | Setup registration area |
|  | Check sound/light equipment and staging before rehearsal |
|  | Hold final rehearsal |

| 1 to 2 Weeks Post Event |
| --- |
|  | Send out event evaluations to all committee members and key school personnel |
|  | Compile evaluation results and share with committee, file for next year |
|  | Send out thank you notes to all VIPs, large donors, corporate sponsors |